## KB Portal - Phased Backlog
Feature Area | Task ID | Title | Component | Feature Description | Priority | Status | Progress % | Assignee | Est. Hours | Start Date | End Date | Sprint/Milestone | Actual Hours | Dependencies | Progress Comment | Blockers/Risks | Acceptance Criteria
Enterprise KB | V1.1 | Foundation : Project scaffold + routing | Frontend | Set up app shell: admin login screen (mock/local auth, no backend), main layout, routing to KB list page. No real auth provider yet. | P1 | Not Started | 0% | Ashok | 6 | 2026-06-24 | 24-Jun-2026 | v1 |  | None | v1 — MVP ¦ Admin login → create KB → upload file → see it persist (localStorage). Crawler = static button only. FOCUS: get the basic flow working in the first few days. |  | Admin can 'log in' (local) and land on KB list page
Enterprise KB | V1.2 | KB List : KB list page (empty state) | Frontend | Page that shows all KBs the admin created. Empty state with 'Create KB' button. Reads from localStorage on load. | P1 | Not Started | 0% | Ashok | 6 | 24-Jun-2026 | 25-Jun-2026 | v1 |  | V1.1 |  |  | Page loads; shows empty state when no KBs exist
Enterprise KB | V1.3 | Create KB : Create KB form (name + description) | Frontend | Modal/form: KB Name + Description. On save, write KB object to localStorage and show it in the list. This is step 1 & 2 of your flow. | P1 | Not Started | 0% | Ashok | 6 | 25-Jun-2026 | 26-Jun-2026 | v1 |  | V1.2 |  |  | Admin creates KB with name+description; appears in list immediately
Enterprise KB | V1.4 | Persistence : localStorage persistence layer | Frontend | Small helper to save/load/delete KBs and their files in localStorage (JSON). Survives refresh. This is step 5 — KBs visible when admin returns. | P1 | Not Started | 0% | Ashok | 6 | 26-Jun-2026 | 29-Jun-2026 | v1 |  | V1.3 |  |  | After refresh/return, all created KBs are still visible
Enterprise KB | V1.5 | KB Detail : KB detail page | Frontend | Click a KB → go inside. Shows KB name, description, list of uploaded files, an Upload button, and a (static) Crawl Site button. | P1 | Not Started | 0% | Ashok | 6 | 29-Jun-2026 | 30-Jun-2026 | v1 |  | V1.4 |  |  | Clicking a KB opens its detail page with file list + upload area
Enterprise KB | V1.6 | Upload : File upload UI + store in KB | Frontend | Inside a KB: pick file(s), show file name/size/type, save file metadata to that KB in localStorage. This is step 3 — upload + show file. | P1 | Not Started | 0% | Ashok | 8 | 30-Jun-2026 | 02-Jul-2026 | v1 |  | V1.5 |  |  | Uploaded file shows in the KB's file list and persists on refresh
Enterprise KB | V1.7 | Upload : Upload progress animation | Frontend | Show an animation/visual while the file is 'being processed' (queued→processing→done states, even if simulated). This is the 'show what it's doing' part. | P1 | Not Started | 0% | Ashok | 6 | 02-Jul-2026 | 03-Jul-2026 | v1 |  | V1.6 |  |  | User sees animated states while file uploads; ends in Done
Enterprise KB | V1.8 | Crawler (stub) : Static 'Crawl Site' button + depth field | Frontend | Add a Crawl Site button and an 'n levels' depth input — VISUAL ONLY, no real crawling. This is step 4 — show the static button, don't wire it. | P1 | Not Started | 0% | Sreepad | 4 | 25-Jun-2026 | 26-Jun-2026 | v1 |  | V1.5 | Intentionally non-functional in v1 |  | Crawl button + depth input visible; clicking shows 'coming soon'
Enterprise KB | V1.9 | KB Mgmt : Edit / delete KB | Frontend | Let admin rename, edit description, or delete a KB. Update localStorage accordingly. | P1 | Not Started | 0% | Sreepad | 5 | 26-Jun-2026 | 29-Jun-2026 | v1 |  | V1.5 |  |  | Admin can edit/delete a KB; list updates and persists
Enterprise KB | V1.10 | Polish : Empty/loading/error states + styling | Frontend | Tidy empty states, loading spinners, simple validation (no blank KB name), consistent styling with tfGPT palette. | P1 | Not Started | 0% | Sreepad | 6 | 29-Jun-2026 | 30-Jun-2026 | v1 |  | V1.6,V1.9 |  |  | Clean UX; no blank names; looks consistent
Enterprise KB | V1.11 | Demo : Wire demo flow + sample data | Frontend | End-to-end demo: login → create 2 KBs → upload files → refresh → all persist. Seed optional sample KB for Sonu demo. | P1 | Not Started | 0% | Sreepad | 4 | 30-Jun-2026 | 02-Jul-2026 | v1 |  | V1.10 |  |  | Full v1 flow demoable in <5 min; data persists across refresh
Enterprise KB | V2.1 | Backend : Move localStorage → real DB + API | Backend | Replace localStorage with PostgreSQL KB registry + REST APIs (create/list/update/delete KB, upload file). Migrate v1 UI to call APIs. | P1 | Not Started | 0% | Sreepad |  |  |  | v2 |  | v1 done | v2 — Add intelligence & real backend ¦ Pull these in AFTER v1 is solid. Move from localStorage to real DB, real processing. |  | KBs/files persist in DB via API; UI unchanged for user
Enterprise KB | V2.2 | Ingestion : Real website crawler (wire the button) | Backend | Make the v1 static crawler real: register URL, crawl up to n levels, respect robots.txt, ingest pages. | P1 | Not Started | 0% | Sreepad |  |  |  | v2 |  | V2.1 |  |  | Crawl button actually crawls n levels and stores pages
Enterprise KB | V2.3 | Enrichment : Text extraction + OCR pipeline | Backend | Extract text from PDF/DOCX/PPTX/images; OCR for scanned docs. Replace simulated processing with real. | P1 | Not Started | 0% | Sreepad |  |  |  | v2 |  | V2.1 |  |  | Uploaded files get real extracted text stored
Enterprise KB | V2.4 | Enrichment : LLM summaries + entity extraction | Backend | Vision-LLM summaries, entity & relationship extraction per document. | P1 | Not Started | 0% | Sreepad |  |  |  | v2 |  | V2.3 |  |  | Each doc has summary + entities visible in UI
Enterprise KB | V2.5 | Artifacts : Vector index + wiki articles + entities | Backend | Build vector index per KB; auto-generate wiki articles; entity registry. | P2 | Not Started | 0% | Sreepad |  |  |  | v2 |  | V2.4 |  |  | Wikis + entities generated and browsable
Enterprise KB | V2.6 | Search : pgvector → hybrid + pluggable stores | Backend | Semantic search (pgvector) then hybrid (vector+BM25); pluggable providers (Pinecone, OpenSearch, Qdrant, Azure AI). | P1 | Not Started | 0% | Sreepad |  |  |  | v2 |  | V2.5 |  |  | Search returns relevant results; provider swappable per KB
Enterprise KB | V2.7 | Governance : Audit logging + per-KB isolation + SharePoint | Backend | Audit logs for all events; enforce per-KB access; SharePoint as a source. | P1 | Not Started | 0% | Sreepad |  |  |  | v2 |  | V2.1 | Entra ID app reg needed |  | Events logged; users see only authorized KBs
Enterprise KB | V2.8 | Frontend : UI for summaries, entities, search, audit | Frontend | Surfaces v2 backend: enrichment detail, entity views, search UI, audit log viewer. | P1 | Not Started | 0% | Ashok |  |  |  | v2 |  | V2.4,V2.6 |  |  | All v2 backend features visible & usable in UI
Enterprise KB | V3.1 | Ingestion : Full sources + artifact registry | Backend | All source types + external artifact registry (URL-based assets, versioning). | P2 | Not Started | 0% | TBD |  |  |  | v3 |  | v2 done | v3 — Advanced , Furthest out. Only after v2 metrics justify it. |  | Artifacts registered by URL+metadata; agents can locate them
Enterprise KB | V3.2 | Enrichment : Vision-LLM for diagrams/UML/flowcharts | Backend | Deep visual understanding of architecture diagrams, UML, flowcharts, SmartArt. | P2 | Not Started | 0% | TBD |  |  |  | v3 |  | V3.1 |  |  | Diagrams understood semantically, not just OCR'd
Enterprise KB | V3.3 | Artifacts : Knowledge graph | Backend | Full knowledge graph for relationship-based reasoning & retrieval. | P2 | Not Started | 0% | TBD |  |  |  | v3 |  | V3.2 |  |  | Graph supports relationship queries across KB
Enterprise KB | V3.4 | Search : Graph / wiki / context search | Backend | Retrieval strategies: knowledge graph, context graph, wiki, artifact search. | P1 | Not Started | 0% | TBD |  |  |  | v3 |  | V3.3 |  |  | Multiple retrieval strategies selectable
Enterprise KB | V3.5 | Agentic : Multi-source parallel retrieval + fusion/re-rank | Backend | Agents query 2–3 KBs in parallel; retrieval fusion: dedup, re-rank, compress, source attribution. | P1 | Not Started | 0% | TBD |  |  |  | v3 |  | V3.4 |  |  | Agent reasons over merged multi-KB context with citations
Enterprise KB | V3.6 | Governance : Analytics + Confluence/GitHub connectors | Backend | Usage analytics dashboards; Confluence & GitHub as sources. | P2 | Not Started | 0% | TBD |  |  |  | v3 |  | v2 done |  |  | Analytics dashboards live; new connectors ingest content