# Enterprise Knowledge Base Platform

v1 Implementation Document

Prepared for: Sonu
Team: Ashok (Frontend) + Sreepad (Backend)
Timeline: ~6 weeks to v1 demo
Reference: kb-platform-animation.html (6-step architecture walkthrough)

# 1. Executive Summary

We are building an Enterprise Knowledge Base Platform based on the architecture defined in the HTML walkthrough. The platform lets employees upload knowledge, organize it by domain (HR, Engineering, Sales, etc.), and ask questions in natural language — with AI-generated answers backed by source citations.

v1 (6 weeks) delivers the core intelligence layer: ingestion of documents, semantic storage, and agentic search with grounded answers (HTML Step 05).

v2 and v3 add enrichment, connectors, knowledge graph, and enterprise governance (HTML Steps 02, 03, 04, 06).

# 2. Reference Architecture (from HTML Walkthrough)

The HTML file (kb-platform-animation.html) is a 6-scene animated architecture spec. Each scene represents a pipeline stage:

| Step | HTML Title | What It Depicts |
| --- | --- | --- |
| 01 | Ingestion — Capture knowledge from anywhere | Documents (PDF/DOCX/PPTX/XLSX/IMG), Website crawling, Artifacts & URLs → Content ingestion |
| 02 | Enrichment — Understand before you index | OCR, Vision-LLM, Entity extraction, Relationships + summaries |
| 03 | Knowledge artifacts — Turn content into reusable knowledge | Vector index, Wiki articles, Entities, Relationships, Knowledge graph → KB registry |
| 04 | Search framework — Pluggable search, swappable storage | Pinecone, OpenSearch, Qdrant, PGVector, Azure AI Search → Multiple search strategies |
| 05 | Agentic search — The agent reasons over merged knowledge | User query → AI agent → parallel multi-source search → fusion → grounded answer with sources |
| 06 | Governance & growth — Secure, audited, built to extend | KB isolation, audit logging, usage analytics, connector framework (SharePoint, Confluence, etc.) |

Tip for presentation: Open kb-platform-animation.html in a browser and walk through Steps 1–6 live.

# 3. Version Roadmap — What We Achieve When

| HTML Step | v1 (~6 weeks) | v2 (~+8 weeks) | v3 (~+10 weeks) |
| --- | --- | --- | --- |
| 01 Ingestion | Documents upload only | URLs + website crawler | Full sources + artifacts |
| 02 Enrichment | Basic text extraction + OCR | LLM summaries, entities | Vision-LLM for diagrams |
| 03 Knowledge artifacts | Vector index + KB registry | Wiki articles, entities | Knowledge graph |
| 04 Search framework | pgvector semantic search | Hybrid search, pluggable stores | Graph/wiki/context search |
| 05 Agentic search | FULL v1 FOCUS — agent + RAG + citations | Multi-source parallel retrieval | Advanced fusion & re-ranking |
| 06 Governance | Basic per-KB isolation | Audit logging + SharePoint | Analytics + Confluence/GitHub |

# 4. v1 — What We Are Building

## 4.1 v1 Goal

In 6 weeks, deliver a working KB platform where users upload documents, organize them into Knowledge Bases, ask questions in plain English, and receive AI answers with verifiable source citations — covering HTML Steps 01 (partial), 03 (partial), 04 (partial), and 05 (core).

## 4.2 v1 User Journey

LOGIN — User signs in to the portal

CREATE KB — e.g. 'Pre-sales KB', 'HR Policies'

UPLOAD DOCS — PDF, DOCX, PPTX, XLSX, images

PROCESSING — Extract text → chunk → embed → store (automatic)

ASK QUESTION — 'Where is the latest AI sales deck?'

AGENT WORKS — Picks relevant KB(s) → searches vectors → fuses results

GET ANSWER — Grounded response + citations (filename, excerpt, score)

## 4.3 v1 Architecture

Browser → Next.js Frontend → FastAPI Backend → PostgreSQL (metadata) + pgvector (embeddings/search) + OpenAI (embeddings + chat LLM)

## 4.4 v1 Features

| # | Feature | HTML Step |
| --- | --- | --- |
| F1 | User authentication | — |
| F2 | Knowledge Base CRUD | 03 |
| F3 | Document upload (PDF, DOCX, PPTX, XLSX, images) | 01 |
| F4 | Ingestion pipeline (extract → chunk → embed → store) | 01 |
| F5 | Processing status (pending → processing → ready/failed) | 01 |
| F6 | Vector storage (pgvector in Postgres) | 03, 04 |
| F7 | Semantic search | 04 |
| F8 | KB registry agent (auto-select relevant KBs) | 05 |
| F9 | RAG retrieval (top-K chunks) | 05 |
| F10 | Answer fusion (dedup, re-rank, compress) | 05 |
| F11 | Grounded LLM answer | 05 |
| F12 | Citations (filename, excerpt, score) | 05 |
| F13 | Chat UI (per-KB + global) | 05 |
| F14 | Per-KB isolation | 06 |

## 4.5 v1 — NOT Included

Website crawling, URL ingestion

Vision-LLM, entity/relationship extraction

Wiki auto-generation, knowledge graph

Multiple vector DB providers (Pinecone, OpenSearch, etc.)

SharePoint / Confluence / GitHub connectors

Audit logs, usage analytics, SSO

# 5. Complete Task Breakdown

## Phase 0 — Project Setup (Week 1)

0.1 Repo setup, branch strategy, env templates (Both, 0.5d)

0.2 Architecture doc + API contract (Both, 1d)

0.3 Docker Compose: Postgres + pgvector + backend + frontend (Sreepad, 2d)

0.4 Postgres schema: users, KBs, documents, chunks (Sreepad, 2d)

0.5 pgvector extension + vector table design (Sreepad, 1d)

0.6 OpenAI embedder integration (Sreepad, 1d)

0.7 OpenAI chat/LLM provider abstraction (Sreepad, 1d)

0.8 Frontend scaffold: Next.js, layout, auth shell (Ashok, 2d)

0.9 Design system: colors, components (Ashok, 2d)

## Phase 1 — Ingestion (Week 1–2) → HTML Step 01

1.1 Auth API: login, token, multi-user (Sreepad, 2d)

1.2 KB CRUD API (Sreepad, 1d)

1.3 Document upload API — multipart, 202 async (Sreepad, 2d)

1.4 Text extraction: PDF, DOCX, PPTX, XLSX, TXT, MD (Sreepad, 2d)

1.5 Image OCR — Tesseract (Sreepad, 1d)

1.6 Chunking service — ~900 chars, 150 overlap (Sreepad, 1d)

1.7 Embed + upsert to pgvector (Sreepad, 2d)

1.8 Document status API + background job queue (Sreepad, 2d)

1.9 Login page (Ashok, 1d)

1.10 KB dashboard: list, create, delete (Ashok, 2d)

1.11 KB detail page + document table (Ashok, 2d)

1.12 Upload zone: drag-drop, progress, status poll (Ashok, 2d)

## Phase 2 — Search & RAG (Week 2–3) → HTML Steps 04 + 05

2.1 Semantic search API: query → embed → pgvector top-K (Sreepad, 2d)

2.2 RAG prompt template + citation extraction (Sreepad, 2d)

2.3 Chat API: single-KB POST /kb/{id}/chat (Sreepad, 2d)

2.4 Search results UI — snippet cards (Ashok, 1d)

2.5 Chat UI: messages, input, loading (Ashok, 3d)

2.6 Citation cards in chat (Ashok, 2d)

## Phase 3 — Agentic Search (Week 3–4) → HTML Step 05 Core

3.1 KB scoring agent: match query to KB name/description (Sreepad, 2d)

3.2 Multi-KB parallel retrieval (Sreepad, 2d)

3.3 Fusion layer: dedup, re-rank, context window (Sreepad, 2d)

3.4 Global chat API: POST /chat (Sreepad, 1d)

3.5 Global chat page — auto KB selection (Ashok, 2d)

3.6 KB badge on citations (Ashok, 1d)

3.7 Empty/error states (Ashok, 1d)

## Phase 4 — Polish & Demo (Week 4–5)

4.1 RAG quality tuning: prompt, top_k, chunk size (Sreepad, 2d)

4.2 Reindex + delete document APIs (Sreepad, 1d)

4.3 Reindex/delete UI actions (Ashok, 1d)

4.4 App header, nav, responsive layout (Ashok, 2d)

4.5 Embed HTML walkthrough as /demo page (Ashok, 1d)

4.6 Sample KBs + test documents for demo (Both, 1d)

4.7 End-to-end smoke test + bug fixes (Both, 2d)

4.8 Setup README + runbook (Both, 1d)

## Phase 5 — Buffer & Cloud Prep (Week 6)

5.1 Production Docker images (Sreepad, 2d)

5.2 AWS deployment guide: RDS, ECS/EC2, S3 (Sreepad, 2d)

5.3 UI fixes from stakeholder feedback (Ashok, 2d)

5.4 v2 backlog document (Both, 1d)

# 6. v2 & v3 — What Comes Next

## v2 (~8 weeks after v1)

Enrichment (Step 02): LLM summaries, entity extraction, relationship tagging

Ingestion expansion (Step 01): URL ingestion, website crawler

Wiki articles (Step 03): Auto-generated from documents

Search upgrade (Step 04): Hybrid search (vector + keyword BM25)

Governance start (Step 06): Audit log (upload, search, access events)

First connector (Step 06): SharePoint (Azure AD OAuth, document sync)

## v3 (~10 weeks after v2)

Knowledge graph (Step 03): Entities + relationships in Postgres

Advanced search (Step 04): Graph, wiki, context search

Full agentic (Step 05): Parallel multi-source retrieval + advanced fusion

Vision-LLM (Step 02): Diagram/table/chart understanding

Connectors (Step 06): Confluence, GitHub, Jira

Enterprise (Step 06): Usage analytics dashboard, SSO/Azure AD

## Full Vision Timeline

| Milestone | Duration | Cumulative |
| --- | --- | --- |
| v1 — Agentic chat + upload | 6 weeks | 6 weeks |
| v2 — Enrichment + SharePoint | 8 weeks | ~3.5 months |
| v3 — Graph + full enterprise | 10 weeks | ~6 months |

# 7. Team, Tech Stack & Prerequisites

## Team

| Person | Role | v1 Ownership |
| --- | --- | --- |
| Ashok | Frontend Lead | All UI: login, KB dashboard, upload, chat, citations, demo page |
| Sreepad | Backend Lead | All API: auth, ingestion, pgvector, agent, RAG, Docker |

## Tech Stack (v1)

| Layer | Technology |
| --- | --- |
| Frontend | Next.js, React, TypeScript, Tailwind CSS |
| Backend | Python, FastAPI, SQLAlchemy |
| Database | PostgreSQL + pgvector |
| AI | OpenAI (text-embedding-3-small + gpt-4o-mini) |
| Queue | Background tasks (Redis/RQ optional) |
| DevOps | Docker Compose (local), AWS (staging post-v1) |

## Prerequisites Before Kickoff

OpenAI API key with billing enabled

GitHub repo created

Postgres with pgvector (via Docker)

6-week allocation for Ashok + Sreepad

Stakeholder demo slot (Week 5–6)

# 8. v1 Success Criteria

1. User logs in securely

2. Creates 2+ Knowledge Bases

3. Uploads PDF/DOCX/PPTX successfully

4. Documents reach 'ready' status

5. Asks natural-language question in chat

6. Agent selects correct KB automatically

7. Answer is relevant and grounded in documents

8. 2+ citations shown with correct filenames

9. Runs locally via Docker Compose

10. HTML walkthrough demo page available at /demo

# 9. Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| OpenAI API costs | Medium | Use gpt-4o-mini; monitor usage |
| RAG answer quality | High | Tune prompts, chunk size, top_k in Week 5 |
| SharePoint complexity (v2) | High | Defer to v2; manual upload in v1 |
| Scope creep | High | Strict v1 sign-off; v2 backlog for extras |
| OCR quality on images | Medium | Clear error messages; optional in v1 |

# 10. One-Line Pitch

"In 6 weeks we deliver an Enterprise KB where employees ask questions in plain English and get AI answers backed by source documents — the foundation for SharePoint, knowledge graph, and full enterprise features."